## Instructions
MS in IT - Spring 2017 - IT Portfolio Management Tool
1. Enter the details required on the Project Worksheet. 'Total Cost to Client' should equal the total cost in the cost benefit analysis submitted for the project. 'Client's IT Budget' should include total IT spending for the current fiscal year. If not available, try to obtain closest estimate for this field. Scaled size of investment is an auto-calculated field that indicates ratio of cost of project to the total IT Budget.
2. On the 'Viability' Worksheet, fill in the 'Score' column with values 0,1,2 or 3 for each risk. Provide your reasoning in the 'Explanation Column'. Use the key provided for the 0 - 3 score. Weighted Score is an auto-field that will be calculated using the 'Weight' and 'Score' columns. The 'Weight' values have been previously populated and may be adjusted to accomodate a unique situation.
3. Once all the scores have been entered, a Viability Index will be calculated to indicate the risk associated with the project. Higher the risk, lower is the viability of the project. The Viability Index will provide the value for the Y axis of the Portfolio Graph. The conversion table gives an insight about how the viability index translates to the corporate discount rate for a project.
4. On the Financial Index sheet: Calculate NPV as a % of the organization's IT Budget, calculate the IRR (using NPV = 0). Enter these and the payback period as a score of 0 - 3 based on the key provided. The weighted score and Finance Index on a scale of 0 - 100 will be calculated by the tool and used as the value on the X axis of the portfolio graph.
5. On the Strategic Fit worksheet, fill in the score column for each criteria listed - provide a value from 0 - 3 based on key provided. The weighted score and the strategic fit index will auto calculate and this value will be used to determine the color of the bubble on the portfolio graph
6. The graph should be created manually or using a charting tool as shown in the Graph worksheet.

## Project
Project Name | AI-Driven Company-Wide Search Engine for Deloitte Resources
Client | Deloitte
Total Cost to Client | 44933
Client's IT Budget | 500000
Relative Size of Investment
Note on B5: ====== ID#AAAB0O5aMIc Daswani, Pooja (2026-02-12 21:39:44) This value be auto calculated and will determine size of circle's radius on graph

## Viability
Instructions: Enter the score for each type of risk, and the explanation for it. (only the values in blue should be entered)
Viability Coefficient | 3.3333
Criteria | Weight | Score (0-3) | Weighted Score | 3 | 2 | 1 | 0 | Explanation
Technology Risk | 2.5 | ---- |  | None | Low | Medium | High
Level of Complexity | 1 | 3 |  | None | Low | Medium | High | Full-stack AI system with NLP, vector search, and React frontend represents high technical complexity
Level of Customization required | 1 | 1 |  | None | Low | Medium | High | Minimal customization needed; leveraging off-the-shelf open-source components (FAISS, Sentence-BERT, FastAPI)
Configuration Detail required | 0.5 | 2 |  | None | Low | Medium | High | Moderate configuration for vector DB indexing, API endpoints, and embedding model tuning
Resource Risk | 2.5 | ---- |  | None | Low | Medium | High
Availability of Resources | 1 | 2 |  | All Available | Some | Almost All | None | 6-person Capstone team with part-time availability; competing academic obligations may limit sustained focus
Skill level of Available Resources | 1 | 3 |  | High | Medium | Low | None | Team includes FinGPT Search Agent architect, AI security researcher, and Deloitte intern with direct domain experience
Cost of training per personnel | 0.5 | 3 |  | No cost | < $ 50 | < $200 | < $1000 | Team already proficient in React, Python/FastAPI, NLP, and cloud deployment; no external training budget required
Organizational Complexity | 2.5 | --- |  | None | Low | Medium | High
Percentage of business units affected | 1.25 | 3 |  | 1 | < 50% units | > 50% units | All units | 50-person pilot impacts <0.01% of Deloitte's 460,000+ workforce; minimal organizational disruption
Process Change Required | 1.25 | 2 |  | None | Few | Some | Most/All | Adds a new search interface to existing workflows without replacing current systems; moderate change management for adoption
Implementation Risk | 2.5 | ---- |  | None | Low | Medium | High
Timeline | 1.25 | 1 |  | 0 - 3 months | 3 - 12 months | 12 - 24 months | > 24 months | 9-week Capstone constraint is tight for AI prototype development; mitigated by MVP-first approach and prior FinGPT architectural work
Impact on Existing Systems | 1.25 | 3 |  | None | Low | Medium | High | Standalone prototype scoped to sample data; no integration with production Deloitte systems required
Viability Index (0-100)
The following chart can be used to calculate discount rate from viability index:
Index | Discount Rate
0 - 25 | 20%
25 - 40 | 18%
40 - 50 | 16%
50 - 60 | 14%
60 - 70 | 12%
70 - 80 | 9%
80 - 90 | 7%
90 - 100 | 4%
Note on D23: ====== ID#AAAB0O5aMIo Pooja Daswani (2026-02-12 21:39:44) This provides the value for the Y Axis on the Portfolio Graph

## Financial Index
Instructions: Enter the score for each financial metric (only the values in blue should be entered)
Finance Index Coefficient | 3.3333
Criteria | Weight | Score (0-3) | Weighted Score | 0 | 1 | 2 | 3 | Explanation
NPV (Net Present Value) | 3.5 | 3 |  | 0 - 4% of IT Budget | 4 - 10% of IT Budget | 10 - 25% of IT Budget | > 25% of IT Budget | Calculate under most likely assumptions. Typically, NPV is calculated over a 3 year period.
IRR (Internal Rate of Return) | 3.5 | 3 |  | <= 8% | 8 - 30% | 30 - 100% | > 100% | Calculate by setting above NPV = 0
Payback Period | 3 | 3 |  | >3 Years | <3 Years | <2 years | <1 year | Period between initial investment and recovery of the total investment
Finance Index (1-100)
Note on D8: ====== ID#AAAB0O5aMIk Pooja Daswani (2026-02-12 21:39:44) This provides the value for the X Axis on the Portfolio Graph

## Strategic Fit
Instructions: Enter the score for each criteria, and the explanation for it. (only the values in blue should be entered)
3.3333
Criteria | Weight | Score (0-3) | Weighted Score | 0 | 1 | 2 | 3 | Explanation
Externally Focussed | 5 | --- |  | None | Low | Medium | High
Industry Trends | 1 | 3 |  | No Alignment | Some alignment | Mostly aligned | Totally aligned | AI-powered enterprise search is a dominant industry trend; major consulting firms investing heavily in AI knowledge tools
Innovation in Product/Service | 2 | 3 |  | No Innovation | Some new offerings | Mostly new prod/service | Brand new prod/service | Novel AI-driven semantic search for internal knowledge management; goes beyond keyword search with NLP and vector embeddings
Competitive Advantage | 1 | 2 |  | No change to existing postion | Little + competitive adv | Some + competitive adv | Major competitive adv | Gives Deloitte an internal edge in knowledge retrieval efficiency, but competitors (McKinsey, EY, PwC) are building similar tools
Expansion of Customer Base | 1 | 1 |  | No change | May increase minimally | May increase substantially | Will increase significantly | Internal tool; does not directly expand client base but may indirectly improve client deliverable quality
Internally Focussed | 5 | --- |  | None | Low | Medium | High
Process Improvement | 2 | 3 |  | No process change | May slightly improve some | Will improve many proc. | Major improvements | Directly improves document search and retrieval processes, reducing estimated 2.8 hrs/week lost per employee to inefficient search
Improvement in technology efficiency | 1.5 | 3 |  | None | Low | Medium | High | Replaces fragmented, siloed search tools with a unified AI-powered semantic search platform across document repositories
Employee Satisfaction | 1.5 | 2 |  | None | Low | Medium | High | Improves daily workflow and reduces frustration from failed searches; moderate but meaningful satisfaction impact
Strategic Index (0-100)
Note on D16: ====== ID#AAAB0O5aMIg Pooja Daswani (2026-02-12 21:39:44) This value is mapped to the color of the bubble on the graph representing this project

## Graph
Portfolio Bubble Chart: X-axis = Finance Index (100), Y-axis = Viability Index (~72.5), Bubble color = Strategic Index (~85). Project plots in the high-value, moderate-risk quadrant with a 9% discount rate.