## Unit Test Results
TEST SCRIPT NAME: XBRL Project Database User Interface - Unit Testing Results
Tester: |  | Gino Gervasio / James Wu
Test Case ID | Date | Test Case Title | # Steps | # Executed | # Not Executed* | Failed | # Passed* | Notes
TC-001 | 2010-03-29 | XBRL Project Query | 1 | 1 | 0 |  | 1
TC-002 | 2010-03-29 | XBRL Project-Fields Query | 1 | 1 | 0 |  | 1
TC-003 | 2010-03-29 | XBRL Labels Query | 1 | 1 | 0 |  | 1
TC-004 | 2010-03-29 | XBRL Presentation Query | 1 | 1 | 0 |  | 1
TC-005 | 2010-04-01 | JSON Marshaller | 1 | 1 | 0 |  | 1
TC-006 | 2010-04-01 | Excel Export | 1 | 1 | 0 |  | 1
TC-006 - ReEx-002 | 2010-04-21 | Excel Export | 1 | 1 | 0 |  | 1 | Change in Excel Design
TC-007 | 2010-03-29 | Data Display | 6 | 6 | 0 |  | 6
TC-008 | 2010-03-30 | User Feedback | 6 | 6 | 0 |  | 6
TC-009 | 2010-03-30 | Empty/Non-Existent Files | 3 | 3 | 0 |  | 3
|  | Totals | 22 | 22 | 0 | 0 | 22
* indicates a calculated field

## Integration Testing Results
TEST SCRIPT NAME: XBRL Project Database User Interface - Integration Testing Results
Tester: |  | Anand Patil
Test Case ID | Date | Test Case Title | # Steps | # Executed | # Not Executed* | App # Failed | # Passed* | Notes
TC-011 | 2010-04-08 | Data Display | 6 | 6 | 0 |  | 6 | *Defect: Display does not show 'Processing' when loading data
TC-011 ReEx-002 | 2010-04-19 | Data Display | 6 | 6 | 0 |  | 6 | Defect Fixed
TC-012 | 2010-04-08 | Excel Export | 12 | 12 | 0 |  | 12 | *Defect: Change in Excel Design
TC-012 ReEx-002 | 2010-04-21 | Excel Export | 12 | 12 | 0 |  | 12 | Defect Fixed
|  | Totals | 36 | 36 | 0 | 0 | 36
* indicates a calculated field

## IncidentLog
TEST SCRIPT NAME: XBRL Project Database User Interface - Incident Log
Incident ID | Date Created | Description | Severity | Resolution | Date Fixed | Date Validated
Incident-01 | 2010-04-08 | Processing' Status does not display when page is loading project information | Moderate | Development Team to re-implement display status | 2010-04-19 | 2010-04-19
Incident-02 | 2010-04-09 | Change in Excel Layout; Multiple values should be listed in rows and not in columns | Moderate | Development Team to change layout of Export to Excel functionality. | 2010-04-23 | 2010-04-23

## Percentages
|  | Test Steps | [5 empty] | Incidents Logged |  |  |  |  | Incidents Retested |  |  |  |  | Incidents Open
Test Phases |  | Total | Executed |  | N/S | Fail | Pass | 1- Crit | 2-Ser | 3-Mod | 4-Mi | Total | 1- Crit | 2-Ser | 3-Mod | 4-Mi | Total | 1- Crit | 2-Ser | 3-Mod | 4-Mi | Total
1 | Unit Testing | 22 | 22 | 100% | 0 | 0 | 22 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
2 | Integration Testing | 36 | 36 | 100% | 0 | 0 | 36 | 0 | 0 | 2 |  | 2 | 0 | 0 | 2 |  | 2 | 0 | 0 | 0 |  | 0
|  | 58 | 58 | 100% | 0 | 0 | 58 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0% | 0% | 100% | 0% | 0% | 100% | 0% |  | 0% | 0% | 100% | 0% |  | 0% | 0% | 0% | 0%

## Data (hidden)
Critical
Serious
Moderate
Minor