## Slide 1: CRM Data Quality & Case Routing Optimization
Presenter: Program Team

## Slide 2: Executive Summary
We propose a 10-week initiative to improve CRM data quality and case routing to reduce rework and accelerate customer resolution.
Expected outcomes: higher First Contact Resolution (FCR), lower Average Handle Time (AHT), improved SLA attainment, and better reporting accuracy.
Approach: rapid diagnostic, targeted fixes (taxonomy + validations + routing rules), pilot, then scale with governance.
Decision requested: approve scope, timeline, and resourcing to start 03/11/2026.

## Slide 3: Problem Statement
Current challenges
Inconsistent case categories and free-text fields cause misrouted tickets and repeat touches.
Duplicate customer records and missing mandatory fields reduce agent efficiency and reporting reliability.
Routing rules have grown organically; limited documentation and testing increases regression risk.
Observed impacts
~25% of cases require at least one transfer
Backlog spikes after product releases
Leaders lack confidence in trend reporting and root-cause insights

## Slide 4: Goals, Objectives, and Success Metrics
Business objectives
Reduce avoidable transfers and rework
Improve customer experience and operational efficiency
Establish sustainable data governance for CRM hygiene
Target success metrics
FCR: 62% → 72%
AHT: 9.0 min → 8.0 min
Transfer rate: 25% → 15%
SLA attainment (24-hr response): 89% → 94%
“Unknown/Other” category usage: 18% → <5%

## Slide 5: Proposed Scope
In scope
Case taxonomy redesign (categories, subcategories, definitions)
Field standardization and validation rules (required fields, picklists)
Routing rules optimization (skill-based routing, exception handling)
Duplicate record triage approach (rules + workflows; limited cleanup)
Reporting enhancements (core KPI definitions + dashboards)
Governance design (owners, cadence, change control)
Out of scope (for this phase)
Full CRM platform migration
Contact center telephony replacement
Enterprise master data management (MDM) implementation
Large-scale historical data remediation beyond agreed rules

## Slide 6: Proposed Approach and Workplan
Phase 1: Discover & Diagnose (Weeks 1–2)
Stakeholder interviews (Ops, CRM admin, Analytics, Compliance)
Data profiling (completeness, duplicates, category usage)
Baseline KPIs and pain-point quantification Deliverables: diagnostic readout, baseline KPI pack, prioritized backlog
Phase 2: Design (Weeks 3–4)
Taxonomy design workshops + definitions
Validation and routing rule design; test scenarios Deliverables: taxonomy dictionary, rules design spec, test plan
Phase 3: Build & Pilot (Weeks 5–7)
Configure fields/validations/routing in sandbox
Pilot with 1–2 queues; agent feedback loop Deliverables: configured solution, pilot results, refined rules
Phase 4: Deploy & Stabilize (Weeks 8–10)
Production release + hypercare
Dashboard rollout + governance launch Deliverables: release notes, training artifacts, governance charter

## Slide 7: Deliverables
Current-state diagnostic and KPI baselines
Case taxonomy (definitions, examples, do/don’t guidance)
CRM configuration package (fields, validations, routing rules)
Test plan + results (including edge cases)
Pilot readout with measured impact and recommendations
Dashboards for FCR, AHT, SLA, transfers, backlog drivers
Governance toolkit: RACI, change control, monthly data quality scorecard
Training materials: agent quick reference + admin runbook

## Slide 8: Timeline and Milestones
Start: 03/11/2026 End: 05/17/2026
Key milestones
Week 2: Diagnostic complete; backlog prioritized
Week 4: Taxonomy + routing/validation design approved
Week 7: Pilot complete; go/no-go decision for scale
Week 8: Production deployment begins
Week 10: Stabilization complete; governance in steady state

## Slide 9: Assumptions, Dependencies, and Risks
Assumptions
Access to CRM sandbox and production release windows
Ops leaders provide SMEs for workshops (2–3 hrs/week)
Analytics data sources are available and reliable enough for baseline
Dependencies
Security/compliance review turnaround (target: <5 business days)
IT change management calendar and freeze periods
Vendor/telephony integration constraints (if applicable)
Top risks + mitigations
Stakeholder misalignment on taxonomy → structured workshops + decision log
Routing changes disrupt operations → phased pilot + rollback plan
Data quality issues larger than expected → prioritize “top drivers” first, plan Phase 2

## Slide 10: Commercials
Estimated duration: 10 weeks Estimated effort: ~300–450 hours (blended) Resourcing
PM: 0.5 FTE
CRM Admin/Engineer: 0.75 FTE
Analyst: 0.5 FTE
Change Lead: 0.25 FTE
SMEs: 2–4 hrs/week (Ops + Compliance)
Cost drivers
Number of queues and routing complexity
Volume of fields/validations and integration touchpoints
Testing rigor and release constraints
*Numbers are illustrative placeholders—replace with your estimate model.

## Slide 11: Decisions Needed & Next Steps
Decisions requested
Confirm in-scope items and success metrics
Approve timeline (start date + pilot scope)
Confirm named Product Owner and SME availability
Immediate next steps (Week 0–1)
Kickoff meeting + finalize governance cadence
Provision access (sandbox, data extracts, reporting tools)
Schedule workshops (taxonomy, routing, compliance)
First 2-week outputs
Baseline KPI pack + pain-point prioritization
Draft taxonomy v1 + quick wins list